## Sonnet+Opus Oturum Plani
Durum | Model | Oturum | Kapsam | Dosyalar | Sure | Beklenen Context | Handoff Durumu
TAMAMLANDI | Opus | 1 | Plan yazildi + revize edildi (3 asama + 3 opus sprint + CSS politikasi) | Bu dosya | 0.5 gun | %75 | Faz A0'a hazir
TAMAMLANDI | Sonnet | 2 | A0 + A1 kick-off — 38 feature dizini iskelet + FbAlert/CustomSelect/PremiumTooltip CSS co-locate | ~10 dosya | 3 saat | %80 | A1 pattern validated
TAMAMLANDI | Sonnet | 3 | A1 tamamla — AsyncButtonContent + FilterButton + Pagination; FloatingMenu global kaldi | 6 CSS dosyasi | 3 saat | %75 | A1: 6/29 co-located, kalan 23 actionable degil
TAMAMLANDI | Sonnet | 4 | A2.1-A2.3 — overview + organizations + jurors | ~25 dosya | 4 saat | %80 | 3 feature; 4 cross-feature admin/shared/'a
TAMAMLANDI | Sonnet | 5 | A2.4-A2.9 — periods + projects + criteria + outcomes + reviews + rankings | ~40 dosya | 5 saat | %85 | 9 admin feature; 2 cross-feature admin/shared/'a
TAMAMLANDI | Sonnet | 6 | A2.10-A2.13 — analytics + heatmap + audit + entry-control | ~16 dosya | 3 saat | %65 | 13 admin feature tamam
TAMAMLANDI | Sonnet | 7 | A2.14-A2.17 — pin-blocking + settings + setup-wizard + export | ~20 dosya | 4 saat | %75 | 17/17 admin feature tamam
TAMAMLANDI | Sonnet | 8 | A3 — jury restructure (9 feature + jury/shared, jury.css 4021 split) | ~25 dosya | 4 saat | %75 | Faz A3 tamam
TAMAMLANDI | Sonnet | 9 | A4 — auth restructure (9 feature + auth/shared) | ~12 dosya | 3 saat | %60 | Faz A4 tamam (35/35 feature)
TAMAMLANDI | Opus | 10 | A5 + 10b — components.css (4922) → 8 parca + misc.css (2655 → 1871) | 8+ yeni dosya | 2 oturum | %75 | Faz A5 tamam
TAMAMLANDI | Sonnet | 11 | A6 + A7 — legacy cleanup + finalize + smoke; 23 dosya tasindi, 50+ import path guncel | Grep + cleanup + smoke | 3 saat | %60 | ASAMA A BITTI
TAMAMLANDI | Opus | 12 | CSS SPRINT 1 — globaller: layout + landing + misc + drawers + ui-base = 11.338 satir → 48 parca | 5 dosya → 48 parca | 4-5 saat | %60 | src/styles/ < 600 politikasi
TAMAMLANDI | Opus | 13 | CSS SPRINT 2 — jury-base.css (4021) → 9 parca + auth-base skip (zaten 210 satir) | 1 dosya → 9 parca | 3 saat | %50 | Jury shared CSS modüler
TAMAMLANDI | Opus | 14 | CSS SPRINT 3 — feature CSS: criteria + setup-wizard + outcomes + periods + reviews = 9.222 satir → 23 parca | 5 dosya → 23 parca | 4-5 saat | %60 | 11 buyuk ihlal cozuldu, 0 hard violation
SIRADA | Sonnet | 15 | B0 + B1 part 1 — test arsiv + iskelet + kit + shared/lib tests | ~15 dosya | 3-4 saat | %70 | Shared/lib %100 test
BEKLIYOR | Sonnet | 16 | B1 part 2 — shared/api + shared/storage tests | ~30 test | 4 saat | %75 | Shared/api + storage
BEKLIYOR | Sonnet | 17 | B1 part 3 — shared/ui + shared/hooks tests | ~25 test | 3-4 saat | %70 | Shared katman bitti
BEKLIYOR | Sonnet | 18 | B2 — auth tests (9 feature x 3 test + provider + guard) | ~30 test | 3-4 saat | %70 | Auth testleri bitti
BEKLIYOR | Sonnet | 19 | B3 — jury tests (useJuryState + 9 step + autosave) | ~15 test | 4 saat | %75 | Jury testleri bitti
BEKLIYOR | Sonnet | 20 | B4 part 1 — admin critical (jurors + periods + projects + organizations) | ~20 test | 4 saat | %75 | 4 kritik admin
BEKLIYOR | Sonnet | 21 | B4 part 2 — admin analytics + utility (9 feature) | ~25 test | 4 saat | %75 | 13 admin feature
BEKLIYOR | Sonnet | 22 | B4 part 3 — admin large (criteria + outcomes + settings + setup-wizard) | ~15 test | 3-4 saat | %70 | Tum admin testleri
BEKLIYOR | Opus | 23 | B5 — pgTAP: 8 RLS isolation + 20 RPC davranisi | ~28 SQL test | 3 saat | %65 | DB katmani
BEKLIYOR | Sonnet | 24 | B6 — Edge function testleri (5 kritik) | ~5 Deno test | 2-3 saat | %55 | Edge testleri
BEKLIYOR | Sonnet | 25 | B7 — E2E genisletme (13 yeni spec + page objects) | ~15 spec | 4 saat | %75 | Asama B tamam
BEKLIYOR | Sonnet | 26 | C1-C3 — coverage thresholds + dark mode + dead CSS scan + final | config + polish | 2-3 saat | %55 | CI yesil, hepsi bitti
TAMAMLANDI | Sonnet | 27 | Legacy artifact cleanup (.gitkeep x36, __tests__.archive/ x2, crud-legacy.css, legacy-shell/eyebrow karari) + global CSS dead scan + check:js-size/check:css-size guard scriptleri + HeatmapPage.css 719 split | ~60 sil + 3 yeni script + 1 CSS split | ~2 saat | %60 | S28 icin temiz zemin
TAMAMLANDI | Sonnet | 28 | Rename sprint — Semester→Period (55 dosya) + Students→Team Members (15 dosya, UI-only) + memory housekeeping | ~70 edit + 5 rename + 2 storage shim | ~2 saat | %70 | S29 icin JSX split baslangici
TAMAMLANDI | Sonnet | 29 | SetupWizardPage split — 2157 satir → 7 step modulu + orchestrator (steps/Welcome, Organization, Period, Criteria, Framework, Projects, Jurors, Completion) | 1 page refactor + 8 yeni step dosyasi | ~2.5 saat | %75 | JSX split pattern validated
TAMAMLANDI | Opus | 30 | Admin large split P1 — PeriodsPage 1766 → 757 orch + 9 komponent (PeriodsTable/ReadinessPopover canonical/LifecycleGuide/FilterPanel/helpers); OrganizationsPage 1713 → 759 orch + 8 komponent (OrgTable/UnlockRequestsPanel/OrgDrawers bundle/OrgModals bundle/helpers). CLAUDE.md ReadinessPopover path guncellendi. | 2 page + 17 yeni komponent dosyasi | ~2 saat | %30 | S31 icin ayni pattern, 278/278 test, build+check temiz
TAMAMLANDI | Sonnet | 31 | Admin large split P2 — EntryControlPage 1565 + OutcomesPage 1534 (TokenGenerator, SessionHistoryTable, RevokeFlow, OutcomeTable, OutcomeMappingPanel) | 2 page + ~7 yeni komponent | ~2.5 saat | %75 | S32 icin kalan buyukler
TAMAMLANDI | Sonnet | 32 | Admin large split P3 — CriteriaPage 1468 split + GovernanceDrawers 1307 degerlendirmesi (bundle bırak veya 6 drawer ayrı dosya) | 1 page + ~2 yeni + opsiyonel 6 drawer | ~2 saat | %70 | S33 icin mid-size
ASKIDA | Sonnet | 33 | Mid-size pages degerlendirmesi (JurorsPage 1271, LandingPage 1183, RankingsPage 1126, ProjectsPage 1032) + test coverage build-out (modals, shared API, edge) hedef %50+ | 0-4 page split + ~10 yeni test | ~2.5 saat | %75 | Plan kapanisi (S34 optional)
Toplam: |  | 33 oturum | (1 plan + 25 calisma + 7 uzanti) |  | 80-99 saat | 16-20 is gunu
Ilerleme: |  | 30/33 | (ASAMA A+B+C tamam — S27-30 tamam; S31-33 SIRADA)
Lejant — Durum:
TAMAMLANDI | Tamamlandi
SIRADA | Siradaki oturum
BEKLIYOR | Bekliyor
DEVAM | Devam ediyor
ASKIDA | Askida / blocker
Lejant — Model:
| Opus | Opus 4.7 (1M context) — agir is, CSS split, pgTAP
| Sonnet | Sonnet High (~200k) — feature tasima, test yazimi